## WBS Outline
WBS OUTLINE - Horizon 2020
PROJECT TITLE | Horizon 2020- Step Towards Crime Free India | COMPANY | CDAC Knowledge Park Bangalore
PROJECT Team | Ashwini Choure,Abhishek Palo, Sunny Kumar,Debjit Mishra | DATE | 2018-01-15
PROJECT TITLE
1 | Data Collection |  |  | Estimate in Hrs | Assigned To | Cumulative Effort in Hrs | Comments
1.1 | Data files for Crime against women 2001 until 2013
1.1.1 | District Wise data for crime against women |  |  | 2 | Team | 2
1.2 | Data files for Crime against opressed classes
1.2.1 | District Wise data for crime against opressed classes |  |  | 2 | Team | 4
1.3 | Data files for Crime against children
1.3.1 | District Wise data for crime against children |  |  | 2 | Team | 6
1.4 | Human Rights violation
1.4.1 | District Wise data for human rights violation in general |  |  | 2 | Team | 8
2 | Data Preprocessing
2.1 | Pre-processing of data for crime against women
2.1.1 | Clean & Merge of different casing of state and district names to single entity . |  |  | 10 | Team | 16
2.2 | Pre-processing of data for crime against opressed classes
2.2.1 | Clean & Merge of different casing of state and district names to single entity . |  |  | 10 | Team | 26
2.3 | Pre-processing of data for crime against children
2.3.1 | Clean & Merge of different casing of state and district names to single entity . |  |  | 10 | Team | 36
2.4 | Pre-processing of data on Human rights violation
2.4.1 | Clean & Merge of different casing of state and district names to single entity . |  |  | 10 | Team | 48
3 | Descriptive Analysis through Tableau and Python
3.1 | Statistical summary of crime data through 2001 to 2013
3.1.1 | Descriptive analysis of crime data using Tableau charts (Bullet Graph,Pie chart, Bar charts , Geospatial Map chart) |  |  | 40 | Team | 76
3.1.2 | Descriptive analysis of crime data using python Pandas framework and plotting through MatPlotLib |  |  | 60 | Team | 136
4 | Predictive Analysis through ML (Logistic Regression Arima model)
4.1 | Predictive analysis of crime data through 2001 to 2013 for 2014-2016
4.1.1 | Forecasting of Crimes against women |  |  | 40 | Team | 176
4.1.2 | Forecasting of Crimes against children |  |  | 40 | Team | 216
4.1.3 | Forecasting of Crimes against opressed classes |  |  | 40 | Team | 256
5 | Prescriptive Analysis and Reporting
5.1. | Prescriptive analysis of crimes in India
5.1.1 | Optimisation of ML models for overall crime data |  |  | 60 | Team | 316
5.1.2 | Final Prescriptive reports |  |  | 24 | Team | 340
6 | Task
6.1 | Statistical summary of crime data through 2001 to 2013
3.4.1 | Subtask
3.4.2 | Subtask